## Effort Estimation Tasks
Task Number (M1) | Summary of tasks | Estiamte (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Implementors | Estimator:
1 (M1) | Edit Home Page | 1 | 2.66 | 0.33 | Brian Kim, Joshua Omori | 1 (Brian), 2 (Josh)
2 (M1) | Edit Login, Sign up, and Change Password Page | 1 | 4 | 2.5 | Darilyn Evangelista, Brian Kim | 4 (Brian), 2.5 (Darilyn)
3 (M1) | Add My Store Page | 8 | 4 | 4 | Andrew Narciso, Yuhang Wu | Andrew Narciso
4 (M1) | Add the Merch Detail Page | 3 | 2.3 | 0.7 | Yuhang Wu | Yuhang Wu
5 (M1) | Add User Landing Page | 0.15 | 0.1 | 0 | Brian Kim, Yuhang Wu | 0.25 (Brian)
6 (M1) | Add Admin's Home Page | 0.5 | 0.5 | 0 | Yuhang Wu | Yuhang Wu
7 (M1) | Design and set up a database. | 5 | 4.2 | 0.6 | Yuhang Wu | Yuhang Wu
8 (M1) | Edit Footer and Header | 5 | 4 | 3 | Andrew Narciso, Yuhang Wu | Andrew Narciso
9 (M1) | Add Support Page | 3 | 2.5 | 1 | Joshua Omori | Joshua Omori
10 (M1) | Edit the Logout Page | 1 | 0.5 | 0.1 | Yuhang Wu | Yuhang Wu
11 (M1) | Add the Add Merch Page | 4 | 5 | 1 | Yuhang Wu | Yuhang Wu
12 (M1) | Add View Listing | 3 | 2 | 1 | Joshua Omori | Joshua Omori
13 (M1) | Implement notification for login authentication result | 2 | 1.2 | 0.3 | Yuhang Wu | Yuhang Wu
14 (M1) | Design an icon for Wonkes | 1 | 0.1 | 1.5 | Yuhang Wu | Yuhang Wu
15 (M1) | Edit the Merch Detail Page | 0.1 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
16 (M1) | Edit Merch Photo Storage | 3 | 2.6 | 0.5 | Yuhang Wu | Yuhang Wu
17 (M1) | Create card that will be used for listings | 3 | 4 | 0 | Joshua Omori | Joshua Omori
18 (M1) | Migrate Login Credential System | 48 | 8 | 2 | Yuhang Wu | Yuhang Wu
19 (M1) | Fix and improve previous merges to the main branch | 0.5 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
20 (M1) | Deploy to Vercel | 2 | 1.8 | 0.2 | Yuhang Wu | Yuhang Wu
21 (M1) | Add Image Preview for the Add Merch Page | 10 | 0.5 | 1.5 | Yuhang Wu | Yuhang Wu
22 (M1) | Innovate the Add Merch Page | 1 | 0.5 | 0 | Yuhang Wu | Yuhang Wu
23 (M1) | Final Touch Ups for M1 | 2 | 6 | 0 | Joshua Omori | Joshua Omori
24 (M1) | Edit Navbar | 0.5 | 0.6 | 0 | Yuhang Wu | Yuhang Wu
25 (M1) | Fix Wrong GitHub Repo Name | 0.1 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
26 (M1) | Delete My Page | 0.1 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
27 (M1) | Improve Add Merch Form | 2 | 3 | 0.5 | Yuhang Wu | Yuhang Wu
28 (M1) | Validate UH Email Address | 0 | 0 | 0 | Yuhang Wu | Yuhang Wu
29 (M1) | Add Construction Ongoing Page | 0.5 | 0.1 | 0.1 | Yuhang Wu | Yuhang Wu
| Total Hours: | 110.45 | 60.56 | 20.83
Task Number (M2) | Summary of tasks | Estiamte (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Implementors | Estimator:
1 (M2) | Edit Wonkes page | 10 | 14 | 2 | Darilyn Evangelista, Yuhang Wu | Yuhang Wu
2 (M2) | Delete My Page | 0.5 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
3 (M2) | Fix Wrong GitHub Repo Name | 0.5 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
4 (M2) | Validate UH Email Address | 3.5 | 0.65 | 0.1 | Yuhang Wu | Yuhang Wu
5 (M2) | Improve Add Merch Form | 3.5 | 3.5 | 0.5 | Yuhang Wu | Yuhang Wu
6 (M2) | Edit Navbar | 0.5 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
7 (M2) | Improve My Store Page | 4.5 | 2.5 | 0.5 | Yuhang Wu, Joshua Omori | Yuhang Wu
8 (M2) | Reduce Page Loading Time | 5.5 | 5.5 | 1 | Yuhang Wu | Yuhang Wu
9 (M2) | Add Reset Forgotten Password Feature Part 1 | 5 | 6 | 1 | Yuhang Wu | Yuhang Wu
10 (M2) | Add Edit Merch Form | 6 | 6.5 | 1.5 | Yuhang Wu | Yuhang Wu
11 (M2) | Edit 404 Not Found Page | 1 | 1 | 0.2 | Yuhang Wu | Yuhang Wu
12 (M2) | Add Construction Ongoing Page | 1 | 0.7 | 0.1 | Yuhang Wu | Yuhang Wu
13 (M2) | Fix All Broken and Buggy Links | 2.5 | 2.3 | 0.2 | Yuhang Wu | Yuhang Wu
14 (M2) | Add Email User Feature | 10 | 3 | 1 | Yuhang Wu | Yuhang Wu
15 (M2) | Add Reset Forgotten Password Feature Part 2 | 5 | 0.5 | 0 | Yuhang Wu | Yuhang Wu
16 (M2) | Landing Page UI Fix | 3 | 2.8 | 0.2 | Darilyn Evangelista | Darilyn Evangelista
17 (M2) | Add My Favorite Feature | 4 | 5.5 | 1 | Joshua Omori | Joshua Omori
18 (M2) | Add Like Implementation for Merch Detail + fix UI of View Listings and Liked Listings | 3 | 2 | 0.2 | Joshua Omori | Joshua Omori
19 (M2) | Make Fininshing Touches | 2 | 2 | 0 | Joshua Omori | Joshua Omori
| Total Hours: | 71 | 58.75 | 9.5
Task Number (M3) | Summary of tasks | Estiamte (hours) | Coding Effort (hours) | Non-Coding Effort (hours) | Implementors | Estimator:
1 (M3) | Implement Playwright “availability” tests for all pages | 40 | 16 | 4 | Andrew Narciso | Andrew Narciso
2 (M3) | Fix size of sign up page | 1 | 0.9 | 0 | Darilyn Evangelista | Darilyn Evangelista
3 (M3) | Update Webpage Info design in Support to look more complete | 1.5 | 2 | 0.25 | Darilyn Evangelista | Darilyn Evangelista
4 (M3) | Improve listing card | 2.5 | 1 | 2 | Brian Kim | Brian Kim
5 (M3) | Make username case-insesitive | 0.5 | 1 | 1 | Brian Kim, Joshua Omori | Joshua Omori
6 (M3) | Image system overhaul | 2 | 1 | 2 | Brian Kim | Brian Kim
7 (M3) | Add method to delete listings (by own user/any admin) | 6 | 2 | 0 | Yuhang Wu | Yuhang Wu
8 (M3) | Finish Get Seller's Contact in Merch Panel | 5 | 0.5 | 0 | Yuhang Wu | Yuhang Wu
9 (M3) | Cancel button in edit listings should take you back to admin/added listings page | 0.5 | 0.1 | 0 | Yuhang Wu | Yuhang Wu
10 (M3) | Final smash | 12 | 12.3 | 1 | Yuhang Wu | Yuhang Wu
11 (M3) | Find Bugs that are currently plauging the site | 2 | 2.5 | 0.2 | Yuhang Wu, Joshua Omori | Yuhang Wu
12 (M3) | Add Pagenation to Likes and View Listings | 6 | 3 | 0.3 | Joshua Omori | Joshua Omori
13 (M3) | Change Admin Page | 10 | 13 | 1 | Joshua Omori | Joshua Omori
14 (M3) | Add Pagination and Search to Admin Panel | 2 | 1 | 0 | Joshua Omori | Joshua Omori
15 (M3) | Fix Stock Status | 2 | 1 | 0 | Joshua Omori | Joshua Omori
16 (M3) | Changing page number manually gives edit access for all merch | 1.5 | 0.5 | 0 | Joshua Omori | Joshua Omori
17 (M3) | Add method to delete own account | 1 | 1.5 | 0.2 | Joshua Omori | Joshua Omori
| Total Hours: | 95.5 | 59.3 | 11.95
| Grand Total Hours: | 276.95 | 178.61 | 42.28

## Team Effort Experience
Team Member | Software Development Experience (months) | How was coding effort tracked | How was non-coding effort tracked?
Joshua Omori | 48 | M1: Best Estimated Guess; M2/M3: Tracked time spent per session and added it to total | M1: Best Estimated Guess; M2/M3: Tracked time spent per session and added it to total
Darilyn Evangelista | 30 | M1/M2/M3: Google stopwatch | M1/M2/M3: Google stopwatch and estimation
Andrew Narciso | 36 | M1/M2/M3: Estimation | M1/M2/M3: Estimation
Brian Kim | 72 | M1: Estimate; M2/M3: Casual time tracking with a clock | M1: Estimate; M2/M3: Casual time tracking with a clock
Yuhang Wu | 10.5 | M1/M2/M3: Read the clock and take approximate the time elapsed during coding. | M1/M2/M3: Personal feeling, daydreaming, etc.